## Consolidated Estimates
Tasks | Time Estimate (hrs)
Google API for walk time | 4
MBTA API for transport | 4
Lyft API object/button | 4
Uber API object/button | 4
Save state from previous story | 1
Set up map (using google maps) | 4
Plotting routes on map | 5
Design page functions (back and restart) | 2
Page Layout | 3
Possible link to Uber/Lyft app or book through site if on mobile | 8 |  | **check if possible
Total | 39 | -> around 40 hr

## Jacqueline
Tasks | Estimate
1. given inputs from user story 2 | 1 hour. Completed in user story 2
2. Uber button | 5 hours
3. Lyft button | 5 hours
4. MBTA transit route | 5 hours
5. Use google API to set up the following:
- map graphic | 3 hours
- locations on map | 1 hour
- walking time/directions | 2 hours
- narrow down based on preferences from story 2 | 1 hour
6. Configure potential links to Uber/Lyft app | 6 hours
7. navigation buttons on page | 3 hours
Total: | 32 hours

## Faisal
Task | Time Estimate
Configure APIs | 7
Set up / request access | 2
Integrate (get) | 5
- Data | 3
- View (buttons) | 2
View | 10
Route on map | 4
Back / restart buttons | 2
list choices | 4
Route | 12
Back button routes to options page | 1
Restart button routes to story 2 | 1
Choices | 10
- route to individual apps | 4
- integrate booking ?? | 6
Total
| 29 | -> 30 hrs

## Dixon
User Story 3
# | Task Description | Estimate
1 | add map to front page | 1 hour
2 | add button for Uber | 0.5 hours
3 | add button for Lift | 0.5 hours
4 | add button to link MBTA route info | 0.5 hours
5 | design map to display routes | 2 hours
6 | design info table for user to see options | 2 hours
7 | add "new search" button at bottom | 0.5 hours
8 | link "new search" button to restart app | 0.5 hours
9 | add "edit preferences" button at bottom | 0.5 hours
10 | link "edit preferences" button to bring user back to options screen | 0.5 hours
| Total | 8 1/2 hours

## Hana
Tasks | Time Estimate(hrs)
API work
- Google | 3
- MBTA | 3
- Lyft | 3
- Uber | 3
Page Design
Configure page with map | 8
Make layout look nice | 3
Functionality
Back button | 2
Reset button | 2
Get and use state from previous page | 1
Total | 28

## Justin
making the Find the transport screen with a map | 4 hrs
transfer the data from last screen to differernt routing option api(may be store the searching histoty to user database) | 1 hr
use uber api to create a buttom with time estimation, cost est (and transfer to the uber app if mobile) | 6 hrs
use lyft api to create a buttom with time estimation, cost est (and transfer to the uber app if mobile) | 8 hrs
google place api for walking option with time est (and public transportation optoin?) | 4 hrs(+2 hrs)
limebike | 3 hrs
ploting routes of every chosed option to the map | 6 hrs
redirect to next screen upon users next move(done, new search or edit current information) | 5 hrs
estimate total | 37 hrs